## Estimation Summary
Project Overwatch — Build Time Estimation
2-Week Sprints · Agent 24/7 · Human 2hr/day Review · As of July 2026
Key Parameters
Agent Operating Schedule | 24 hours/day, 7 days/week, 365 days/year — autonomous coding, testing, infra provisioning, documentation
Human Review Window | 2 hours/day (14 hours/sprint) — architectural decisions, security sign-offs, regulatory compliance, UX approval
Sprint Duration | 2 weeks (14 calendar days, 10 working days)
Agent Capacity per Sprint | 336 hours/sprint (24×14) — effectively unlimited for task execution, constrained by sequential dependencies
Human Capacity per Sprint | 14 hours/sprint — the primary bottleneck for review-gated milestones
Concurrent Streams | Up to 8 parallel build streams; agent context-switches across them; dependency graph determines start ordering
Production Cutover Goal | 56–60 weeks (28–30 sprints) from project kickoff
MVP | Name | Streams | Sprints | Calendar Weeks | Agent Hours | Human Hours | Key Deliverable
MVP 1 | Foundation & Single-Rail Real-Time Screening | A, B, C, D, H | 6 | 1–12 | 1680 | 84 | K8s cluster, PostgreSQL/Kafka/Redis/MinIO, 27-entity schema, TME rules + sanctions screening, Keycloak RBAC, CI/CD pipeline. Fiat transaction screening live.
MVP 2 | Stablecoin Ingest & Blockchain Analytics | E, B, D | 5 | 13–22 | 1100 | 55 | 6-chain blockchain indexer (ETH/Polygon/Arbitrum/Optimism/Base/Solana), wallet-analytics-adapter (TRM/Chainalysis), graph schema (Apache AGE), risk-scoring-service. Stablecoin screening live.
MVP 3 | Compliance Workflows | F, G | 6 | 23–34 | 1440 | 72 | Travel Rule gateway (Temporal), case-management-service (alert→case→STR lifecycle), forensic-audit-service (tamper-proof ledger, WORM, Merkle trees), AML Admin Portal (dashboard, alert queue, case list). Full alert-to-STR lifecycle.
MVP 4 | Portal, Reporting & STR Filing | G, F | 4 | 35–42 | 920 | 46 | Full AML Admin Portal (investigation workspace, network graph visualisation, SAR drafting, rule config), regulatory-reporting-service (JFIU STREAMS2, HKMA returns), audit log viewer, forensic verifier UI. Production AML portal complete.
MVP 5 | T+1 Batch Scanning | I | 5 | 43–52 | 1200 | 60 | Airflow DAG + batch-scanning-service, 10 parallel K8s analysis Jobs (behavioural baselining, peer group, structuring, velocity, graph anomaly, ensemble ML, rule retrospective, cross-rail layering, sanctions retrospective, SAR pre-population), Daily AML Briefing, batch alert CMS integration. Full T+1 coverage.
MVP 6 | Hardening, Penetration Testing & Cutover | H | 4 | 53–60 | 800 | 56 | Full penetration test + remediation, 500 TPS load test, chaos engineering, CIS hardening >90%, external vendor go-live (TRM, Chainalysis, Notabene, LexisNexis), JFIU STREAMS2 filing live, production cutover, HKMA audit documentation pack.
| TOTAL | All 8 Streams | 30 | 60 weeks | 7140 | 373 | Full converged AML platform — fiat + stablecoin, real-time + T+1 batch, HKMA compliant
Agent vs. Human Hours Breakdown
Category | Agent Hours | % of Total | Human Hours | % of Total | Ratio
Infrastructure & CI/CD (Stream A) | 500 | 7% | 50 | 13.4% | 10:1
Data Layer & Schema (Stream B) | 600 | 8.4% | 30 | 8% | 20:1
Transaction Monitoring Engine (Stream C) | 550 | 7.7% | 35 | 9.4% | 15.7:1
Sanctions & Risk Scoring (Stream D) | 400 | 5.6% | 25 | 6.7% | 16:1
Blockchain Indexing & Wallet Analytics (Stream E) | 450 | 6.3% | 20 | 5.4% | 22.5:1
Compliance Workflows (Stream F) | 800 | 11.2% | 65 | 17.4% | 12.3:1
AML Admin Portal (Stream G) | 900 | 12.6% | 55 | 14.7% | 16.4:1
Integration, Testing & Security (Stream H) | 720 | 10.1% | 50 | 13.4% | 14.4:1
T+1 Batch Scanning (Stream I) | 1220 | 17.1% | 60 | 16.1% | 20.3:1
TOTAL | 6140 | 100% | 390 | 100% | 15.7:1
Key Insight: Why Agent 24/7 Makes This Feasible
• The agent provides 336 hours of work per sprint vs. 14 hours of human review — a 24:1 capacity ratio.
• With 8 parallel streams, the agent context-switches continuously, eliminating idle time between dependent tasks.
• Human time is concentrated on high-leverage review gates: architectural decisions (~30%), security sign-offs (~20%), regulatory compliance (~25%), UX approval (~15%), and vendor liaison (~10%).
• The critical path (A→B→C→F→G = 28 sprints) is constrained by sequential dependencies, not agent throughput. Agent 24/7 ensures no stream is ever blocked waiting for coding capacity.
• Without agent 24/7, a team of 20 engineers working 40hr/week would need ~18–24 months. Agent 24/7 with 2hr/day human steering compresses this to ~14 months.
• Risk: if human review falls behind (illness, competing priorities), the entire schedule slips linearly — each day of missed review delays dependent streams by one day.

## Task Breakdown
Detailed Task Breakdown — Agent Hours, Human Hours & Sprint Allocation
Task ID | Task Group | Tasks | Agent Hours | Human Hours | Calendar Days (Agent) | Review Gates | Start Sprint | End Sprint | MVP
A.1 | K8s Cluster Provisioning | 8 tasks | 80 | 12 | 10 | Network topology, HSM config | 1 | 2 | MVP 1
A.2 | Stateful Infrastructure (PG/Kafka/Redis/MinIO/Temporal/Keycloak) | 7 tasks | 90 | 14 | 12 | DB sizing, retention policies | 1 | 3 | MVP 1
A.3 | CI/CD & Developer Tooling (GitLab/ArgoCD/Vault) | 10 tasks | 120 | 10 | 10 | Pipeline design review | 2 | 3 | MVP 1
A.4 | Security Foundation (HSM/mTLS/WAF/CIS) | 6 tasks | 60 | 14 | 8 | HSM procurement, mTLS policy | 2 | 4 | MVP 1
B.1 | aml_core Schema (27 tables, 6 domains) | 15 tasks | 120 | 10 | 10 | Schema design review, regulatory alignment | 3 | 4 | MVP 1
B.2 | aml_audit Schema (append-only audit) | 4 tasks | 30 | 4 | 4 | Audit log design sign-off | 3 | 4 | MVP 1
B.3 | aml_forensic Schema (WORM, 9 tables) | 10 tasks | 80 | 8 | 8 | Forensic architecture review | 3 | 5 | MVP 1
B.5 | Kafka Infrastructure (11+ topics) | 5 tasks | 40 | 4 | 5 | Topic topology review | 3 | 4 | MVP 1
B.6 | Canonical Transaction Schema (22-field Pydantic) | 5 tasks | 60 | 6 | 6 | Schema standardisation review | 3 | 4 | MVP 1
C.1 | tme-engine (rule core, sliding windows, decision engine) | 12 tasks | 140 | 16 | 12 | Rule DSL design, threshold calibration | 4 | 6 | MVP 1
C.2 | Rule Library (9 initial detection rules) | 9 tasks | 60 | 8 | 8 | Rule logic + false positive review | 5 | 6 | MVP 1
D.1 | sanctions-service (fuzzy matching, OFAC loading) | 9 tasks | 90 | 12 | 10 | Matching algorithm, vendor data feed | 4 | 6 | MVP 1
H.1 | API Integration (7 endpoints, OpenAPI spec) | 8 tasks | 60 | 8 | 6 | API contract review | 5 | 6 | MVP 1
H.3p | Testing — Unit + Integration (core services) | 5 tasks | 60 | 6 | 6 | Test plan approval | 5 | 6 | MVP 1
E.1 | blockchain-indexer (6 chains, Go workers) | 12 tasks | 200 | 12 | 15 | Archive node access, chain config | 7 | 9 | MVP 2
E.2 | wallet-analytics-adapter (TRM/Chainalysis/Redis) | 8 tasks | 100 | 10 | 10 | Vendor API onboarding, rate limiting | 8 | 10 | MVP 2
B.4 | aml_graph Schema (Apache AGE, 5 graph tables) | 6 tasks | 60 | 6 | 6 | Graph model design review | 7 | 8 | MVP 2
D.2 | risk-scoring-service (8 factors, tier escalation) | 7 tasks | 80 | 10 | 8 | Risk model calibration, tier logic | 7 | 9 | MVP 2
C.3 | tme-ml (ONNX, XGBoost, SHAP, shadow-mode) | 8 tasks | 90 | 10 | 10 | ML model governance, shadow-mode review | 8 | 10 | MVP 2
H.3p2 | Testing — Contract + E2E (blockchain + risk) | 4 tasks | 50 | 6 | 5 | Test scenario review | 9 | 11 | MVP 2
F.1 | travelrule-gateway (Temporal, Notabene, IVMS101) | 7 tasks | 120 | 14 | 12 | Travel Rule policy, vendor integration | 12 | 14 | MVP 3
F.2 | case-management-service (4 workflows, REST API) | 10 tasks | 160 | 18 | 14 | Workflow state machine, SLA rules | 12 | 15 | MVP 3
F.4 | forensic-audit-service (hash-chain, Merkle, WORM, witness) | 11 tasks | 150 | 14 | 12 | Forensic architecture, crypto design | 13 | 15 | MVP 3
G.1 | Portal Foundation (Next.js, Keycloak, shadcn/ui) | 5 tasks | 80 | 8 | 8 | UI architecture, design system | 13 | 14 | MVP 3
G.2 | KPI Dashboard (8 KPIs, Recharts, export) | 10 tasks | 100 | 10 | 10 | KPI selection, HKMA alignment | 14 | 16 | MVP 3
G.3 | Alert Queue & Detail (paginated, filterable, 360 view) | 4 tasks | 80 | 8 | 8 | UX review, performance validation | 15 | 16 | MVP 3
G.4 | Case Management UI (investigation workspace, graph viz) | 8 tasks | 160 | 14 | 12 | UX workflow review, Cytoscape design | 18 | 20 | MVP 4
G.5 | Configuration & Admin (rules, thresholds, users, audit) | 5 tasks | 80 | 8 | 8 | Admin UX, audit viewer design | 19 | 20 | MVP 4
G.6 | Reporting Module (SAR generation, HKMA returns) | 3 tasks | 60 | 6 | 6 | Report template review | 19 | 20 | MVP 4
F.3 | regulatory-reporting-service (SAR XML, Airflow DAGs) | 5 tasks | 100 | 12 | 10 | JFIU STREAMS2 schema, HKMA format | 17 | 19 | MVP 4
H.2 | External Vendor Integrations (TRM, Chainalysis, Notabene, LexisNexis) | 6 tasks | 40 | 20 | 10 | DPA execution, vendor onboarding | 18 | 20 | MVP 4
I.1 | batch-scanning-service Core + Airflow DAG | 5 tasks | 200 | 16 | 15 | DAG design, pre-flight logic | 22 | 24 | MVP 5
I.2 | 10 Parallel K8s Analysis Jobs (behavioural, peer, ML, graph, etc.) | 10 tasks | 400 | 20 | 18 | Per-analysis logic review, model validation | 23 | 26 | MVP 5
I.3 | Batch Alert Generation & CMS Integration | 6 tasks | 120 | 8 | 8 | Alert dedup logic, priority rules | 24 | 26 | MVP 5
I.4 | Daily AML Briefing & Reporting | 5 tasks | 80 | 8 | 6 | Briefing template, email notification | 25 | 26 | MVP 5
I.5 | Batch-Specific DB Schema (5 tables, TimescaleDB, 4 Kafka topics) | 6 tasks | 60 | 4 | 5 | Hypertable chunk config, retention | 22 | 23 | MVP 5
I.6 | Batch Pipeline Testing (E2E, unit, failure, performance) | 4 tasks | 100 | 10 | 10 | SLA validation, test data review | 25 | 26 | MVP 5
H.3f | Testing — Full Campaign (E2E, load, chaos, security) | 6 tasks | 120 | 16 | 12 | Test results review, acceptance | 27 | 29 | MVP 6
H.4 | Security Hardening (pentest, CIS, WORM verify, docs) | 7 tasks | 80 | 24 | 14 | Pentest findings, compliance doc sign-off | 27 | 30 | MVP 6
CUT | Production Cutover (staged rollout, DR test, HKMA submission) | 5 tasks | 60 | 16 | 10 | Go/no-go decision, regulatory filing | 29 | 30 | MVP 6
| TOTAL ALL TASKS | 260+ tasks | 3380 | 392 |  |  |  | 30 sprints

## Sprint Timeline
Project Overwatch — 30-Sprint Gantt Timeline (60 Weeks, ~14 Months)
MVP 1: Foundation ¦ MVP 2: Stablecoin ¦ MVP 3: Compliance ¦ MVP 4: Portal ¦ MVP 5: Batch ¦ MVP 6: Hardening
Build Stream | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30
| MVP 1 | [5 empty] | MVP 2 |  |  |  |  | MVP 3 | [5 empty] | MVP 4 |  |  |  | MVP 5 |  |  |  |  | MVP 6
A: Platform & Infrastructure | bar: S1 to S4
B: Core Data Layer | bar: S3 to S6
B: Core Data Layer (cont.) | bar: S7 to S8
C: Transaction Monitoring Engine | bar: S4 to S6
C: TME + ML (cont.) | bar: S8 to S10
D: Sanctions & Risk Scoring | bar: S4 to S6
D: Risk Scoring (cont.) | bar: S7 to S9
E: Blockchain Indexing & Analytics | bar: S7 to S11
F: Compliance Workflows | bar: S12 to S17
F: Regulatory Reporting | bar: S17 to S19
G: AML Admin Portal (core) | bar: S13 to S16
G: AML Admin Portal (full) | bar: S18 to S21
H: Integration, Testing & Security | bar: S5 to S6
H: Extended Testing | bar: S9 to S11
H: Vendor Integrations | bar: S18 to S21
H: Full Test + Security + Cutover | bar: S27 to S30
I: T+1 Batch Scanning | bar: S22 to S26
Calendar Week | W1 | W3 | W5 | W7 | W9 | W11 | W13 | W15 | W17 | W19 | W21 | W23 | W25 | W27 | W29 | W31 | W33 | W35 | W37 | W39 | W41 | W43 | W45 | W47 | W49 | W51 | W53 | W55 | W57 | W59
Key Milestones | bar: W7; W11; W21; W31; W41; W51; W59
|  |  |  | K8s + CI/CD Live |  | Fiat Screening Live |  |  |  |  | Stablecoin Screening Live |  |  |  |  | CMS + Portal Alpha |  |  |  |  | Full Portal + STR Filing |  |  |  |  | T+1 Batch Scanning Live |  |  |  | Production Cutover

## Risks & Sensitivity
Risk Register & Schedule Sensitivity
Risk ID | Risk Description | Impact | Probability | Schedule Impact (Sprints) | Mitigation
R1 | Human review falls behind (illness, competing priorities, decision paralysis) | CRITICAL | Medium | +1 per day of missed review | Escalation protocol; deputy reviewer; pre-approved decision frameworks for routine items; batch review sessions at sprint boundaries
R2 | Blockchain archive node access delayed (vendor procurement, rate limiting) | HIGH | Medium | +2–4 | Start vendor procurement during MVP 1; use public RPC fallback for dev; parallelise node setup across chains
R3 | Vendor API integrations blocked (TRM, Chainalysis, Notabene — legal/DPA delays) | HIGH | High | +3–6 | Mock vendor interfaces for dev/testing; begin DPA negotiation at project kickoff; have fallback vendor options
R4 | HKMA regulatory feedback requires schema/workflow changes | MEDIUM | Medium | +2–4 | Pre-submission review with HKMA liaison; modular architecture allows isolated changes; maintain regulatory change log
R5 | Apache AGE graph performance at scale (>100M edges) degrades | MEDIUM | Low | +2–3 | Benchmark AGE at 10x projected scale during MVP 2; evaluate Neo4j/Dgraph as fallback; graph sharding design pre-planned
R6 | T+1 batch scanning can't meet 4-hour SLA (500K txns) | HIGH | Low | +3–5 | Horizontal K8s Job scaling; Spark as fallback for heavy ML jobs; early SLA testing with synthetic data at MVP 5 start
R7 | Security penetration test finds critical architectural flaw | CRITICAL | Low | +4–8 | Continuous SAST/DAST from Sprint 1; threat modelling review at each MVP boundary; external pentest firm engaged early
R8 | Keycloak/HSM integration complexity exceeds estimate | MEDIUM | Medium | +1–2 | Dedicated IAM spike in Sprint 1; engage HSM vendor professional services; test with softHSM in dev
R9 | Model governance/validation delays (HKMA requires independent model review) | MEDIUM | High | +2–4 | Engage independent model validator during MVP 2 shadow-mode phase; document model development per HKMA supervisory standards
R10 | Scope creep — stakeholders request additional features mid-build | HIGH | Medium | +1–3 per request | Strict MVP gating; feature request backlog for post-MVP 6; change control board with business sponsor sign-off
Schedule Sensitivity Scenarios
Scenario | Description | Human Review (hr/day) | Total Sprints | Total Weeks | vs. Baseline
Best Case | No vendor delays, no scope creep, human review never blocked | 2 | 26 | 52 | -4 sprints (-13%)
Baseline | Planned: 30 sprints with normal risk realisation | 2 | 30 | 60 | Baseline
Moderate Delay | One major vendor delay + minor scope creep on Portal UX | 2 | 34 | 68 | +4 sprints (+13%)
Pessimistic | Two vendor delays, model governance extended, HKMA feedback round | 1.5 | 38 | 76 | +8 sprints (+27%)
Reduced Human (1hr/day) | Human time halved — review gating becomes primary bottleneck | 1 | 42 | 84 | +12 sprints (+40%)
No Human Bottleneck | Hypothetical: human review always available on demand (4hr/day) | 4 | 22 | 44 | -8 sprints (-27%)

## Human Review Budget
Human Review Budget Allocation — 2 Hours/Day, 14 Hours/Sprint
MVP | Sprints | Total Human Hours Available | Architecture Review (30%) | Security Sign-off (20%) | Regulatory & Compliance (25%) | UX & Portal Approval (15%)
MVP 1 | S1–S6 (6) | 84 | 25 | 17 | 21 | 13
MVP 2 | S7–S11 (5) | 70 | 21 | 14 | 18 | 11
MVP 3 | S12–S17 (6) | 84 | 25 | 17 | 21 | 13
MVP 4 | S18–S21 (4) | 56 | 17 | 11 | 14 | 8
MVP 5 | S22–S26 (5) | 70 | 21 | 14 | 18 | 11
MVP 6 | S27–S30 (4) | 56 | 17 | 11 | 14 | 8
TOTAL | 30 sprints | 420 | 126 | 84 | 106 | 64
Daily Review Ritual (2 Hours)
08:00–08:20 | Morning Briefing | Agent presents overnight progress summary across all active streams; review automated CI results and dashboard | No action needed — information only
08:20–08:50 | Decision Gates | Approve/reject items queued overnight: schema changes, security-impacting config, rule logic, API contracts | Human decision required — unblocks agent for next 22 hours
08:50–09:10 | Code Review | Spot-check 2–3 high-impact PRs; review architecture for upcoming work; flag concerns | Guidance given — agent incorporates immediately
09:10–09:30 | Steering & Priorities | Review sprint burndown; reprioritise if needed; assign human tasks (vendor calls, procurement) | Updated sprint plan
09:30–10:00 | Buffer / Deep Dive | Rotating deep dive: Monday=Security, Tuesday=Compliance, Wednesday=UX, Thursday=Performance, Friday=Documentation | Deep dive findings fed to agent